## Sheet1
Dự án | Trang web bán và quản lý cửa hàng thời trang
Công nghệ | Bootstrap + PHP + MySQL
Phạm Minh Đảo - 3119410080
Thành viên | Nguyễn Hà Quốc Bảo - 3119410032 Vũ Đình Dũng - 3119410067 Phan Thanh Du - 3110410061
|  |  |  | September | [25 empty] | October | [30 empty] | November
|  |  |  | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10 | [6 empty] | Week 11 | [6 empty] | Week 12
Task name | Owner | Start date | End date | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27
Design System
Requirements | Bảo,Dũng, Du, Đảo | 2022-09-20 | 2022-09-25 | bar: Week 1 5 to Week 1 11
Draw UML diagram | Bảo,Du | 2022-09-20 | 2022-09-23
Build core Back-end
Import location into DB
Design DB, Build core Front-end | Dũng, Đảo | 2022-09-23 | 2022-09-28
WEB FOR ADMINISTRATION Implement / Coding for Authentication, Authorization, Admin Module
Build master layout(Header, Body, Footer, Sidebar/Navbar) | Đảo | 2022-09-28 | 2022-10-05
UI for Sign-in |  | 2022-09-28 | 2022-10-05
UI for Manage other admin |  | 2022-09-28 | 2022-10-05
UI for Manage users |  | 2022-09-28 | 2022-10-05
UI for Order Management |  | 2022-09-28 | 2022-10-05
UI for Revenue management |  | 2022-09-28 | 2022-10-05
UI for Product Management |  | 2022-09-28 | 2022-10-05
UI for Category Management |  | 2022-09-28 | 2022-10-05
UI for Import and export warehouse |  | 2022-09-28 | 2022-10-05
Integrate API to Front-end | Bảo | 2022-10-05 | 2022-10-10
API for Sign-in |  | 2022-10-05 | 2022-10-10
API for Manage other admin |  | 2022-10-05 | 2022-10-10
API for Manage users |  | 2022-10-05 | 2022-10-10
API for Order Management |  | 2022-10-05 | 2022-10-10
API for Revenue management |  | 2022-10-05 | 2022-10-10
API for Product Management |  | 2022-10-05 | 2022-10-10
API for Category Management |  | 2022-10-05 | 2022-10-10
API for Import and export warehouse |  | 2022-10-05 | 2022-10-10
WEB FOR USERS
Implement / Coding for Customer
Build master layout(Header, Body, Footer, Sidebar/Navbar) | Du | 2022-10-10 | 2022-10-15
UI for Sign-up, Sign-in, Forgot password |  | 2022-10-10 | 2022-10-15
UI for Customer Imformation |  | 2022-10-10 | 2022-10-15
Integrate API to Front-end |  | 2022-10-10 | 2022-10-15
API for Sign-up, Sign-in, Forgot password | Dũng | 2022-10-10 | 2022-10-15
Implement / Coding for Homepage Interface
Build master layout(Header, Body, Footer, Sidebar/Navbar) | Du | 2022-10-15 | 2022-10-20
UI for Advertisement |  | 2022-10-15 | 2022-10-20
UI for Search |  | 2022-10-15 | 2022-10-20
Ui for Category |  | 2022-10-15 | 2022-10-20
UI for Customer Imformation |  | 2022-10-15 | 2022-10-20
UI for Purchase history |  | 2022-10-15 | 2022-10-20
Integrate API to Front-end |  | 2022-10-15 | 2022-10-20
API for Advertisement | Dũng | 2022-10-20 | 2022-10-25
API for Search |  | 2022-10-20 | 2022-10-25
API for Category |  | 2022-10-20 | 2022-10-25
API for Check Login, Logout |  | 2022-10-20 | 2022-10-25
API for Customer Imformation |  | 2022-10-20 | 2022-10-25
API for Purchase history |  | 2022-10-20 | 2022-10-25
Implement / Coding for Product and buy Product
UI for Product Homepage | Đảo | 2022-10-25 | 2022-11-05
UI for Product Detail |  | 2022-10-25 | 2022-11-05
UI for Comment Product |  | 2022-10-25 | 2022-11-05
UI for Payment order |  | 2022-10-25 | 2022-11-05
UI for Waiting for order confirmation |  | 2022-10-25 | 2022-11-05
Integrate API to Front-end |  | 2022-10-25 | 2022-11-05
API for Product Homepage | Bảo | 2022-11-05 | 2022-11-10
API for Product Detail |  | 2022-11-05 | 2022-11-10
API for Comment Product |  | 2022-11-05 | 2022-11-10
API for Payment Order |  | 2022-11-05 | 2022-11-10
API for Waiting for order confirmation |  | 2022-11-05 | 2022-11-10